## Authentication
Menu | Sub Menu | Screen | Form | Input Field | Type | Mandatory | Validation
Login | Login | Login Screen | Login Form | Username | Text | Yes | Email/Mobile
Login | Login | Login Screen | Login Form | Password | Password | Yes | Min 8 chars
Login | OTP | OTP Screen | OTP Form | OTP | Number | Yes | 6 digit
Login | Forgot Password | Reset | Reset Form | Email | Text | Yes | Registered
Login | Reset Password | Reset | Reset Form | New Password | Password | Yes | Strong
TSK ID | Feature | Task | Acceptance Criteria | API | DB
AUTH-01 | Login | Login API | JWT generated on valid login | /api/login | users
AUTH-02 | OTP | OTP Verify | OTP validated | /api/otp | otp_logs
AUTH-03 | Reset | Forgot Password | Reset link sent | /api/forgot | users
AUTH-04 | Security | Session Mgmt | Auto logout works | Middleware | sessions

## Dashboard
Menu | Sub Menu | Screen | Form | Input Field | Type
Dashboard | Admin | Dashboard | Filter | Date Range | Date
Dashboard | PMU | Dashboard | Filter | Project | Dropdown
Dashboard | Vendor | Dashboard | Filter | Status | Dropdown
TSK ID | Feature | Task | Acceptance Criteria | API | DB
DASH-01 | Admin Dashboard | KPI View | All KPIs visible | /api/dashboard | analytics
DASH-02 | Vendor Dashboard | Vendor Data | Vendor-specific data | /api/vendor-dashboard | analytics
DASH-03 | PMU | Semi-Admin | Vendor manage/task monitoring | /api/pmu-dashboard | analytics
DASH-04 | Alerts | Notification | Alerts visible | /api/alerts | notifications
KPI | Role View | Source Module | Calculation | Alert
Total Projects | Admin | Work Order | Count | -
Active Projects | Admin/PMU | Work Order | Status Active | -
Completion % | Admin | Progress | Avg Progress | < Target
Pending Bills | Finance | Billing | Count | > Limit
under-performance Inspections | Admin | Inspection | Count | > 0
Vendor Performance | Admin | KPI | Score-based | Low rating

## RBAC-Matrix
Role | Module | Create | View | Edit | Delete | Approve
Admin | All Modules | Yes | Yes | Yes | Yes | Yes
PMU | Work Order | Yes | Yes | Yes | No | Yes
Vendor | Progress | Yes | Yes | No | No | No
Finance | Billing | Yes | Yes | Yes | No | Yes
Inspector | Inspection | Yes | Yes | Yes | No | Yes
TSK ID | Feature | Task | Acceptance Criteria | API | DB
RBAC-01 | Role | Create Role | Role created | /api/role | roles
RBAC-02 | Permission | Assign Permission | Access works | /api/permission | permissions
RBAC-03 | User | Create User | User mapped to role | /api/user | users
RBAC-04 | Security | Access Control | Unauthorized blocked | Middleware | -

## Dahboard-RBAC-1
Module | Menu Name | Sub Menu | Screen Name | Form Name | Input Fields | Field Type | Mandatory | Validation | Remarks
Authentication | Login | Login | Login Screen | Login Form | Username | Text | Yes | Valid format | Email/Mobile
Authentication | Login | Login | Login Screen | Login Form | Password | Password | Yes | Min 8 chars
Authentication | Login | OTP Verify | OTP Screen | OTP Form | OTP | Number | Yes | 6 digit | Optional (2FA)
Authentication | Login | Forgot Password | Reset Screen | Reset Form | Email/Mobile | Text | Yes | Registered only
Authentication | Login | Reset Password | Reset Screen | Reset Form | New Password | Password | Yes | Strong password
Dashboard | Dashboard | Admin Dashboard | Dashboard | Filter Form | Date Range | Date | No
Dashboard | Dashboard | Admin Dashboard | Dashboard | Filter Form | Project | Dropdown | No
Dashboard | Dashboard | Vendor Dashboard | Dashboard | Filter Form | Status | Dropdown | No
RBAC | User Management | Create User | User Form | User Form | Name | Text | Yes
RBAC | User Management | Create User | User Form | User Form | Email | Text | Yes | Unique
RBAC | User Management | Create User | User Form | User Form | Role | Dropdown | Yes | Admin/Vendor/etc
RBAC | Role Management | Create Role | Role Form | Role Form | Role Name | Text | Yes | Unique
RBAC | Role Management | Permission Mapping | Permission Screen | Permission Form | Module Access | Checkbox | Yes
RBAC | Role Management | Permission Mapping | Permission Screen | Permission Form | Action Rights | Checkbox | Yes | Create/Edit/View/Delete
TSK ID | Module | Feature | Task | Acceptance Criteria | UI Screen | API | DB Table | Role | Est. Hrs
TSK-00 | Authentication | Login | Develop Login API | Valid login with JWT token | Login Screen | /api/login | users | Backend | 6
TSK-00.1 | Authentication | OTP | OTP Verification | OTP validates user | OTP Screen | /api/otp | otp_logs | Backend | 4
TSK-00.2 | Authentication | Password Reset | Forgot Password | Reset link sent | Reset Screen | /api/forgot | users | Backend | 4
TSK-01 | Dashboard | Admin Dashboard | KPI Dashboard | Data visible with filters | Dashboard | /api/dashboard | analytics | Frontend | 6
TSK-01.1 | Dashboard | Vendor Dashboard | Vendor View | Vendor-specific data only | Dashboard | /api/vendor-dashboard | analytics | Frontend | 5
TSK-02 | RBAC | Role Creation | Create Roles | Role saved successfully | Role Screen | /api/role | roles | Backend | 4
TSK-02.1 | RBAC | Permission Mapping | Assign Permissions | Role-based access works | Permission Screen | /api/permission | permissions | Backend | 6
TSK-02.2 | RBAC | User Management | Create User | User assigned role | User Screen | /api/user | users | Backend | 5
TSK-02.3 | RBAC | Access Control | Restrict Access | Unauthorized blocked | All Screens | Middleware | - | Backend | 6

## Work_Order
Menu | Screen | Form | Input Field | Type | Mandatory
Work Order | Create WO | WO Form | Work Order No | Text | Yes
Work Order | Create WO | WO Form | Vendor | Dropdown | Yes
Work Order | Create WO | WO Form | Start Date | Date | Yes
Work Order | Create WO | WO Form | End Date | Date | Yes
Work Order | Upload | WO Form | Agreement | File | Yes
TSK ID | Feature | Task | Acceptance Criteria | API | DB
WO-01 | Create WO | Save WO | WO created by system/manual | /api/wo | work_orders
WO-02 | Upload | Agreement Upload | File stored | /api/upload | documents

## Vendor_Execution
Menu | Screen | Form | Input Field | Type
Vendor | Dashboard | Progress | Report Type | Dropdown
Vendor | Dashboard | Progress | Work % | Number
Vendor | Dashboard | Progress | Evidence | File
TSK ID | Feature | Task | Acceptance Criteria | API | DB
VEN-01 | Progress | Submit Report | Data saved | /api/progress | progress_reports

## Inspection
Menu | Screen | Form | Input Field | Type
Inspection | Schedule | Inspection Form | Date | Date
Inspection | Report | Inspection Form | Remarks | Text
TSK ID | Feature | Task | Acceptance Criteria | API | DB
INS-01 | Inspection | Submit Report | Report saved | /api/inspection | inspections

## Financial
Menu | Screen | Form | Input Field | Type
Billing | Bill Entry | RA Bill | Amount | Number
Billing | Bill Entry | RA Bill | Invoice | File
Inspection | Passed | genrate bill | invice format | form
TSK ID | Feature | Task | Acceptance Criteria | API | DB
FIN-01 | Billing | Submit Bill | Bill stored | /api/bill | bills

## DMS
Menu | Screen | Form | Input Field | Type
DMS | Upload | DMS Form | Document Type | Dropdown
DMS | Upload | DMS Form | File | File
TSK ID | Feature | Task | Acceptance Criteria | API | DB
DMS-01 | Upload | File Upload | File saved | /api/doc | documents

## Communication
Menu | Screen | Form | Input Field | Type
Query | Raise Query | Query Form | Subject | Text
Query | Raise Query | Query Form | Message | Textarea
TSK ID | Feature | Task | Acceptance Criteria | API | DB
COM-01 | Query | Raise Query | Query saved | /api/query | queries